## SkillProof Tracker
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | Core Verification Flow | US1 | As a developer, I want to authenticate with GitHub OAuth so I can start verification securely. | Implement OAuth URL + callback flow in core API and frontend callback page. | Must Have | 8 | Done | Mandatory | Validate /api/auth/github and callback JWT issuance. | Mandatory
|  |  |  | Persist user profile and token claims with secure JWT settings. |  |  |  | Gowtham MS | Token expiry/signature tests and negative token tests. | Gowtham MS
|  | US2 | As a developer, I want to start a verification session by selecting a GitHub repo. | POST /api/verify/start should fetch repo files, filter noise, detect language/framework. | Must Have | 13 | Done | Gowtham MS | End-to-end start verification test using sample repository. | Gowtham MS
|  |  |  | AI gateway call to Python service with authenticated internal secret. |  |  |  | Gowtham MS | Contract test for core-to-AI request and response schema. | Gowtham MS
|  | US3 | As a developer, I want generated questions grounded in my codebase. | FastAPI questions router + question generator with file references. | Must Have | 13 | Done | Gowtham MS | Health + generation endpoint test with real repository context. | Gowtham MS
E2 | Answer Evaluation and Badge | US4 | As a developer, I want my answers evaluated with rubric scores and feedback. | Evaluation router and evaluator service return per-question scoring and feedback. | Must Have | 13 | Done | Harsha | Submit representative answers and verify rubric score ranges. | Gowtham MS
|  | US5 | As a developer, I want a signed public badge proving verification integrity. | Generate badge token and HMAC-SHA256 signature with tamper-evident payload. | Must Have | 8 | Done | Harsha | Signature validation and tamper test on badge payload. | Dattatri
|  |  |  | Expose badge data endpoint for public token-based view. |  |  |  | Harsha | GET /api/badge/{token} functional and security tests. | Dattatri
E3 | Trust and Transparency Signals | US6 | As a recruiter, I want confidence and behavior metadata visible with badge evidence. | Capture tab switches, paste count, and average answer time during verification. | Must Have | 8 | Done | Ganesh | Verify telemetry counters persist and render in badge view. | Dattatri
|  |  |  | Compute confidence tier (High/Medium/Low) server-side and persist in badge. |  |  |  | Ganesh | Confidence-tier unit tests for threshold logic. | Dattatri
|  | US7 | As a recruiter, I want evidence cards per question to inspect answer quality. | Recruiter detail evidence panel with question text, code snippet, answer, feedback, score pills. | Should Have | 8 | Done | Ganesh | UI test for evidence accordion and score badge rendering. | Dattatri
E4 | Phase 2 Scoring Enhancements | US8 | As a hiring manager, I want mixed-mode questions (code + conceptual) with type-level scoring. | Support typed question metadata (CODE_GROUNDED, CONCEPTUAL) through APIs and DB. | Should Have | 13 | Done | Gowtham MS | Type-propagation test across start, submit, badge, recruiter endpoints. | Gowtham MS
|  |  |  | Compute weighted score policy (default 60/40) and expose scoring mode metadata. |  |  |  | Gowtham MS | Weighted scoring regression tests on known answer sets. | Gowtham MS
E5 | Next Phase Hardening | US9 | As a recruiter, I want execution-backed verification signals for stronger trust. | Add optional mini execution tasks and capture pass/fail/timeout/error metadata. | Should Have | 20 | To Do | Harsha | Execution evidence visible and included in integrity score. | Amarendra
|  | US10 | As a recruiter, I want assist-likelihood heuristics without hard-fail cheating claims. | Detect large instant answer jumps, long idle to sudden completion, repeated low-depth/high-accuracy pattern. | Could Have | 13 | To Do | Harsha | Heuristic output visible with explanatory text and low false positives. | Amarendra
|  | US11 | As a recruiter, I want manual review decisions captured in-system. | Add actions: Verified / Needs Live Interview / Reject with notes and timestamped audit trail. | Should Have | 8 | To Do | Harsha | Decision status persistence + export summary validation. | Amarendra
Notes: | MoSCoW
| Must Have | Critical requirements essential for release and platform trust.
| Should Have | High-value requirements that significantly improve quality and hiring confidence.
| Could Have | Useful enhancements with lower immediate delivery impact.
| Won't Have | Out of current release scope; consider in later iterations.
Story Points
| Scale | 0,1,2,3,5,8,13,20
Use points for complexity + effort + risk, capped at 20 for this board.